## Sheet1
Bug ID | Module | Test Case ID | Test Case Description | Issue Summary | Severity | Priority | Status | Screenshot
BUG_001 | Notes Page | TC_006 | Validate Note Title Is Mandatory | Title required message is not displayed. | High | High | Open
BUG_002 | Notes Page | TC_007 | Validate Empty Note Creation | Empty note is created without warning. | High | High | Open
BUG_003 | Notes Page | TC_008 | Validate Long Note Title | No character limit validation for title. | Medium | Medium | Open
BUG_004 | To-Do List | TC_006 | Task Creation Without Title | Task saved with empty title. | High | High | Open
BUG_005 | To-Do List | TC_007 | Task Title Length Exceeding Limit | Excessively long title accepted. | High | Medium | Open
BUG_006 | Dashboard | TC_006 | Dashboard Loading Without Internet | No feedback message shown on connection failure. | High | High | Open
BUG_007 | Dashboard | TC_007 | Stats Update Failure | Stats update inaccurately on external changes. | High | High | Open
BUG_008 | Profile | TC_006 | Error on Invalid Email | Invalid email format accepted. | High | High | Open
BUG_009 | Logout | TC_006 | Logout Without Login | Logout button visible without login. | High | High | Open
BUG_010 | Logout | TC_007 | Logout From Expired Session | No session expired message shown. | High | High | Open
BUG_011 | Logout | TC_008 | Logout on Network Failure | App freezes with no user feedback. | Critical | Critical | Open
BUG_012 | Logout | TC_009 | Logout API Failure | Redirects to login even on API failure with no error. | High | High | Open
BUG_013 | UI | TC_006 | Button Sizes on Mobile | Buttons are too small to interact with. | High | High | Open
BUG_014 | UI | TC_007 | Notebook List View Responsive | Items overlap and layout breaks on smaller viewports. | Critical | Critical | Open
BUG_015 | UI | TC_009 | Horizontal Scrollbar on Mobile | Layout causes horizontal scrolling. | High | High | Open
BUG_016 | UI | TC_011 | Font Size on Small Devices | Text too small and unreadable. | High | High | Open
BUG_017 | Footer | TC_FL_004 | Footer Missing on Dashboard Page | Footer not consistent across modules. | Critical | Critical | Open
BUG_018 | Footer | TC_FL_006 | Broken Link in Footer | Clicking broken link results in 404 page. | Critical | High | Open
BUG_019 | Footer | TC_FL_009 | Horizontal Scrollbar in Footer | Mobile layout causes scrollbar. | High | High | Open
BUG_020 | Footer | TC_FL_010 | Footer Text Alignment | Footer icons/text misaligned. | Medium | Medium | Open
BUG_021 | Footer | TC_FL_005 | Footer Not Mobile Responsive | Footer elements do not stack on mobile properly. | High | High | Open
BUG_022 | Profile | TC_004 | Profile Update Not Reflecting | Changes in name/email not saved or reflected. | Medium | High | Open
BUG_023 | Dashboard | TC_003 | Navigation to Notes Not Working | Navigation button doesn’t work. | Medium | High | Open
BUG_024 | Dashboard | TC_004 | Profile Info Not Displayed on Dashboard | User info missing from Dashboard UI. | Medium | Medium | Open
BUG_025 | Notes Page | TC_005 | Note Image Upload Fails | Image upload fails with no feedback. | High | High | Open
BUG_026 | Profile | TC_005 | Profile Picture Upload Not Working | Upload doesn't work and shows no error. | High | High | Open
BUG_027 | Profile | TC_003 | Edit Profile Button Not Working | Fields not editable after clicking "Edit." | Medium | Medium | Open
BUG_028 | Logout | TC_010 | Clicking Logout Twice | No safeguard on double click, could cause issues. | High | Medium | Open
BUG_029 | Profile | TC_002 | Profile Info Not Visible | Basic info missing from UI. | Medium | Medium | Open
BUG_030 | Notes Page | TC_004 | Note Deletion Not Working | Note remains visible after delete. | High | High | Open
BUG_031 | Dashboard | TC_005 | Dashboard Customization Not Saved | Custom settings are not persistent after refresh. | Medium | Medium | Open